## Workplan Summary
Workplan |  | Application Identifier: | 2024/FMP/0004 | Project Title: | Upgrade and construction of Maintown levee
Project Summary
No. | Milestone |  | Start | Finish
1 | Review Environmental Factors and permits |  | 28/02/2025 | 13/06/2025
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Conduct Review Environmental Factors (REF) | 28/02/2025 | 13/06/2025 | 30167 | 15083 | 0 | 45250
| 2 | Fisheries permit approved | 28/02/2025 | 13/06/2025 | 0 | 0 | 0 | 0
|  |  |  | Total: | 30167 | 15083 | 0 | 45250
No. | Milestone |  | Start | Finish
2 | Site establishment |  | 16/06/2025 | 29/08/2025
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Site establishment | 16/06/2025 | 29/08/2025 | 15333 | 7667 | 0 | 23000
| 2 | Survey set out | 16/06/2025 | 29/08/2025 | 9067 | 4533 | 0 | 13600
|  |  |  | Total: | 24400 | 12200 | 0 | 36600
No. | Milestone |  | Start | Finish
3 | Construction |  | 1/09/2025 | 31/03/2026
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Levee upgrade construction (1500m) and Levee new construction (300m) | ​01/09/2025 | 31/03/2026 | 253333 | 126667 | 0 | 380000
| 2 | Outlet pipes/Drainage | ​01/09/2025 | 31/03/2026 | 16567 | 8283 | 0 | 24850
|  |  |  | Total: | 269900 | 134950 | 0 | 404850
No. | Milestone |  | Start | Finish
4 | Community education |  | 1/04/2026 | ​08/07/2026
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Community education (signage) | ​01/04/2026 | ​08/07/2026 | 1000 | 500 | 0 | 1500
| 2 | Community drop-in session | ​01/04/2026 | ​08/07/2026 | 233 | 117 | 0 | 350
|  |  |  | Total: | 1233 | 617 | 0 | 1850
No. | Milestone |  | Start | Finish
5 | Diversion channel and re-establishment |  | 9/07/2026 | 30/09/2026
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Construction three culverts | ​09/07/2026 | 30/09/2026 | 88433 | 44217 | 0 | 132650
| 2 | Re-establish vegetation (200m2) | ​09/07/2026 | 30/09/2026 | 5833 | 2917 | 0 | 8750
| 3 | Activity for mandatory project measure | ​09/07/2026 | 30/09/2026 | 0 | 0 | 0 | 0
|  |  |  | Total: | 94266 | 47134 | 0 | 141400
|  |  |  | Overall Total: | 419966 | 209984 | 0 | 629950

## Workplan
Workplan |  | Application Identifier: | 2024/FMP/0004 | Project Title: | Upgrade and construction of Maintown levee
Project Outcomes
No. | Outcome | Description
1 | Maintown dam levee construction | To undertake flood mitigation works in the Maintown dam by upgrading 1500m of the existing levee and construction of 300m of new levee.
2 | Community Education | A community education program that will ensure Maintown residents are better aware and informed on flood management options implemented by Council.
Project Schedule
No. | Milestone |  | Start | Finish | Outcome IDs
1 | Review Environmental Factors and permits |  | 28/02/2025 | 13/06/2025 | 1
| No. | Activities | Start | Finish
| 1 | Conduct Review Environmental Factors (REF) | 28/02/2025 | 13/06/2025
| 2 | Fisheries permit approved | 28/02/2025 | 13/06/2025
2 | Site establishment |  | 16/06/2025 | 29/08/2025 | 1
| No. | Activities | Start | Finish
| 1 | Site establishment | 16/06/2025 | 29/08/2025
| 2 | Survey set out | 16/06/2025 | 29/08/2025
3 | Construction |  | 1/09/2025 | 31/03/2026 | 1
| No. | Activities | Start | Finish
| 1 | Levee upgrade construction (1500m) and Levee new construction (300m) | 1/09/2025 | 31/03/2026
| 2 | Outlet pipes/Drainage | 1/09/2025 | 31/03/2026
4 | Community education |  | 1/04/2026 | 8/07/2026 | 2
| No. | Activities | Start | Finish
| 1 | Community education (signage) | 1/04/2026 | 8/07/2026
| 2 | Community drop-in session | 1/04/2026 | 8/07/2026
5 | Diversion channel and re-establishment |  | 9/07/2026 | 30/09/2026 | 1
| No. | Activities | Start | Finish
| 1 | Construction three culverts | 9/07/2026 | 30/09/2026
| 2 | Re-establish vegetation (200m2) | 9/07/2026 | 30/09/2026
| 3 | Activity for mandatory project measure | 9/07/2026 | 30/09/2026
Project Measures
No. | Milestone
5 | Diversion channel and re-establishment
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 1 | Construction three culverts | Managing and delivering the project (include human resourcing for implementation, collaboration, etc)* | Number of grant funded staff | 0 | Number
|  |  |  | Number of hours (grant funded) | 0 | Number
|  |  |  | Number of grant funded consultants/contractors | 15 | Number
|  |  |  | Number of hours (grant funded consultants/contractors) | ​12850 | Number
|  |  |  | Number of non grant funded staff | 2 | Number
|  |  |  | Number hours (non grant funded) | 86 | Number
|  |  |  | Number of volunteers | 0 | Number
|  |  |  | Number of hours (volunteers) | 0 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 2 | Re-establish vegetation (200m2) | Increase understanding of flood issues within the community* | Number of individuals reporting increased awareness of the issue/s | ​125 | Number
|  |  |  | Describe the people included here | Local residents of Maintown catchment | Free Text (5 to 50 words)
|  |  |  | Number of individuals reporting increased understanding of the issue/s | 60 | Number
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 3 | Activity for mandatory project measure | Implement strategies / install structures to mitigate flood risk* | Number of flood mitigation structures constructed/installed | 1 | Number
|  |  |  | Number of properties with reduced flooding and/or reduced flood risk | ​720 | Number
|  |  |  | Number of properties purchased to reduce flood risk | 0 | Number
|  |  |  | Number of properties raised to reduce flood risk | 0 | Number
|  |  |  | Length of new levee constructed | ​300 | Metres
|  |  |  | Length of existing levee reconstructed | ​1500 | Metres
|  |  |  | Number of flood gauges installed | 0 | Number
|  |  |  | Number of new flood warning systems installed | 0 | Number
|  |  |  | Number of properties protected from flooding through project works | ​500 | Number
Project Budget |  | Selected Ratio: | 33% 2:1
|  |  | Whole Total: | 629950 | 0 | 209984 | 419966
No | Milestone
1 | Review Environmental Factors and permits
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Conduct Review Environmental Factors (REF) | Contractor | 45250 | 0 | 15083 | 30167
| 2 | Fisheries permit approved | Non costed activity | 0 | 0 | 0 | 0
|  |  | Total: | 45250 | 0 | 15083 | 30167
No | Milestone
2 | Site establishment
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Site establishment | Contractor | 23000 | 0 | 7667 | 15333
| 2 | Survey set out | Contractor | 13600 | 0 | 4533 | 9067
|  |  | Total: | 36600 | 0 | 12200 | 24400
No | Milestone
3 | Construction
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Levee upgrade construction (1500m) and Levee new construction (300m) | Contractor | 380000 | 0 | 126667 | 253333
| 2 | Outlet pipes/Drainage | Contractor | 24850 | 0 | 8283 | 16567
|  |  | Total: | 404850 | 0 | 134950 | 269900
No | Milestone
4 | Community education
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Community education (signage) | Contractor | 1500 | 0 | 500 | 1000
| 2 | Community drop-in session | Public exhibition attendance | 350 | 0 | 117 | 233
|  |  | Total: | 1850 | 0 | 617 | 1233
No | Milestone
5 | Diversion channel and re-establishment
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Construction three culverts | Contractor | 132650 | 0 | 44217 | 88433
| 2 | Re-establish vegetation (200m2) | Plants 2,500 @ $3.50 | 8750 | 0 | 2917 | 5833
| 3 | Activity for mandatory project measure | N/A | 0 | 0 | 0 | 0
|  |  | Total: | 141400 | 0 | 47134 | 94266