## Workplan
Workplan |  | Application Identifier: | 2020/CEI/00## | Project Title: | Sample Coastal and Estuary Implementation Workplan
Project Outcomes
No. | Outcome | Description
1 | Restore degraded coastal habitats | to improve the resilience of coastal wetlands and littoral rainforests to the impacts of climate change, including opportunities for ecosystem migration
2 | Community engagement and awareness | Gaining the engagement of the community in managing coastal hazards
Project Schedule
No. | Milestone | Start | Finish | Outcome IDs
1 | Define project scope and consultation | 2020-11-16 | 2021-01-29 | 1, 2
| No. | Activities | Activity Type | Start | Finish
| 1 | Design and cost works. | Scoping impact/identifying the risk | 2020-11-16 | 2021-01-29
| 2 | Environmental review of proposed works. | Scoping impact/identifying the risk | 2020-11-16 | 2021-01-29
| 3 | Consult stakeholders regarding proposed works. | Consulting and collaborating | 2020-11-16 | 2021-01-29
| 4 | Publicly exhibit proposal. | Consulting and collaborating | 2020-11-16 | 2021-01-29
| 5 | Finalise proposed works and submit detailed work plan. | Scoping impact/identifying the risk | 2020-11-16 | 2021-01-29
No. | Milestone | Start | Finish | Outcome IDs
2 | Implement bush regeneration activities - Stage 1 | 2021-04-02 | 2021-04-16 | 1
| No. | Activities | Activity Type | Start | Finish
| 1 | Weed control | Regeneration | 2021-04-02 | 2021-04-16
| 2 | Rubbish removal | Regeneration | 2021-04-02 | 2021-04-16
| 3 | Revegetation | Regeneration | 2021-04-16 | 2021-04-16
No. | Milestone | Start | Finish | Outcome IDs
3 | Implement bush regeneration activities - Stage 2 | 2021-04-02 | 2021-04-16 | 1, 2
| No. | Activities | Activity Type | Start | Finish
| 1 | Weed control | Regeneration | 2021-04-02 | 2021-04-02
| 2 | Rubbish removal | Regeneration | 2021-04-05 | 2021-04-14
| 3 | Revegetation | Regeneration | 2021-04-16 | 2021-04-16
| 4 | Follow-up community consultation | Consulting and collaborating | 2021-04-16 | 2021-04-16
No. | Milestone | Start | Finish | Outcome IDs
4 | Final acquittal | 2022-03-31 | 2022-03-31 | 1
| No. | Activities | Activity Type | Start | Finish
| 1 | Submit acquittal documents to DPIE | Regeneration | 2022-03-31 | 2022-03-31
Project Measures
No. | Milestone
4 | Final acquittal
| No. | Activities | Activity Type
| 1 | Submit acquittal documents to DPIE | Regeneration
|  |  | Measure | Expected Output | Unit
|  |  | Area regenerating | 600 | square metres
Project Budget |  | Selected Ratio: | 0.3333
|  |  | Whole Total: | 61000 | 0 | 20333 | 40667
No | Milestone
1 | Define project scope and consultation
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Design and cost works. |  | 500 | 0 | 167 | 333
| 2 | Environmental review of proposed works. |  | 6000 | 0 | 2000 | 4000
| 3 | Consult stakeholders regarding proposed works. |  | 2500 | 0 | 833 | 1667
| 4 | Publicly exhibit proposal. |  | 1500 | 0 | 500 | 1000
| 5 | Finalise proposed works and submit detailed work plan. |  | 1000 | 0 | 333 | 667
|  |  | Total: | 11500 | 0 | 3833 | 7667
No | Milestone
2 | Implement bush regeneration activities - Stage 1
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Weed control |  | 10000 | 0 | 3333 | 6667
| 2 | Rubbish removal |  | 5000 | 0 | 1667 | 3333
| 3 | Revegetation |  | 9000 | 0 | 3000 | 6000
|  |  | Total: | 24000 | 0 | 8000 | 16000
No | Milestone
3 | Implement bush regeneration activities - Stage 2
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Weed control |  | 10000 | 0 | 3333 | 6667
| 2 | Rubbish removal |  | 5000 | 0 | 1667 | 3333
| 3 | Revegetation |  | 9000 | 0 | 3000 | 6000
| 4 | Follow-up community consultation |  | 1500 | 0 | 500 | 1000
|  |  | Total: | 25500 | 0 | 8500 | 17000
No | Milestone
4 | Final acquittal
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Submit acquittal documents to DPIE |  | 0 | 0 | 0 | 0
|  |  | Total: | 0 | 0 | 0 | 0