## Workplan
Workplan |  | Application Identifier: | 2020/CEMP/00## | Project Title: | Sample Coastal and Estuary Planning Workplan
Project Outcomes
No. | Outcome | Description
1 | Produce a CMP | Produce a CMP to set the long-term strategy for the coordinated management of the coast, with a focus on achieving the objects and objectives of the Coastal Management Act 2016 (CM Act).
2 | Community engagement and awareness | Gaining the engagement of the community in managing coastal hazards
Project Schedule
No. | Milestone | Start | Finish | Outcome IDs
1 | Define project scope and engage consultant | 2020-11-16 | 2021-03-29 | 1
| No. | Activities | Activity Type | Start | Finish
| 1 | Inception meeting | Scoping impact / identifying the risk | 2020-11-16 | 2021-02-27
No. | Milestone | Start | Finish | Outcome IDs
2 | Draft Coastal Management Program | 2021-04-02 | 2021-07-16 | 1
| No. | Activities | Activity Type | Start | Finish
| 1 | Literature and information review. | Scoping impact / identifying the risk | 2021-04-02 | 2021-04-30
| 2 | Coastal hazard assessment. | Scoping impact / identifying the risk | 2021-04-02 | 2021-06-16
| 3 | Draft Emergency Action Sub-PlanCoastal ecosystem health assessment. | Scoping impact / identifying the risk | 2021-06-16 | 2021-07-16
| 4 | Identify management options and select preferred options. | Scoping impact / identifying the risk | 2021-05-16 | 2021-07-16
| 5 | Create implementation schedule. | Scoping impact / identifying the risk | 2021-05-16 | 2021-07-16
| 6 | Draft Coastal Zone Management Plan. | Scoping impact / identifying the risk | 2021-05-16 | 2021-07-16
No. | Milestone | Start | Finish | Outcome IDs
3 | Consultation | 2020-11-16 | 2021-12-22 | 1, 2
| No. | Activities | Activity Type | Start | Finish
| 1 | Circulate Draft Coastal Zone Management Plan to stakeholders for comment. | Consulting and collaborating | 2021-04-02 | 2021-04-02
| 2 | Publicly exhibit Draft Coastal Zone Management Plan. | Consulting and collaborating | 2021-04-05 | 2021-07-16
| 3 | Conduct community workshops. | Consulting and collaborating | 2021-04-16 | 2021-07-16
| 4 | Present Draft Coastal Zone Management Plan to Councillors. | Consulting and collaborating | 2021-07-16 | 2021-07-16
No. | Milestone | Start | Finish | Outcome IDs
4 | Finalise Coastal Management Program | 2021-07-16 | 2021-12-22 | 1, 2
| No. | Activities | Activity Type | Start | Finish
| 1 | Summary of changes required provided to consultant. | Consulting and collaborating | 2021-07-16 | 2021-08-16
| 2 | Update Coastal Zone Management Plan in response to comments. | Consulting and collaborating | 2021-08-16 | 2021-08-16
| 3 | Council approval of changes made by consultant. | Consulting and collaborating | 2021-08-16 | 2021-09-08
| 4 | Final Coastal Zone Management Plan submitted to Council. | Scoping impact / identifying the risk | 2021-12-22 | 2021-12-22
No. | Milestone | Start | Finish | Outcome IDs
5 | Final acquittal | 2022-03-31 | 2022-03-31 | 1
| No. | Activities | Activity Type | Start | Finish
| 1 | Submit acquittal documents to DPIE | Consulting and collaborating | 2022-03-31 | 2022-03-31
Project Measures
No. | Milestone
5 | Final acquittal
| No. | Activities | Activity Type
| 1 | Final Coastal Zone Management Plan submitted to Council. | Scoping impact / identifying the risk
|  |  | Measure | Expected Output | Unit
|  |  | Properties covered by a floodplain risk management study and plan | 0 | Number
|  |  | Estuaries covered by a Coastal Management Program | 2 | Number
Project Budget |  | Selected Ratio: | 0.3333
|  |  | Whole Total: | 134850 | 0 | 44950 | 89900
No | Milestone
1 | Define project scope and engage consultant
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Inception meeting |  | 5000 | 0 | 1667 | 3333
|  |  | Total: | 5000 | 0 | 1667 | 3333
No | Milestone
2 | Draft Coastal Management Program
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Literature and information review. |  | 12000 | 0 | 4000 | 8000
| 2 | Coastal hazard assessment. |  | 30000 | 0 | 10000 | 20000
| 3 | Draft Emergency Action Sub-PlanCoastal ecosystem health assessment. |  | 6000 | 0 | 2000 | 4000
| 4 | Identify management options and select preferred options. |  | 25000 | 0 | 8333 | 16667
| 5 | Create implementation schedule. |  | 2000 | 0 | 667 | 1333
| 6 | Draft Coastal Zone Management Plan. |  | 12000 | 0 | 4000 | 8000
|  |  | Total: | 87000 | 0 | 29000 | 58000
No | Milestone
3 | Consultation
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Circulate Draft Coastal Zone Management Plan to stakeholders for comment. |  | 500 | 0 | 167 | 333
| 2 | Publicly exhibit Draft Coastal Zone Management Plan. |  | 2500 | 0 | 833 | 1667
| 3 | Conduct community workshops. |  | 12000 | 0 | 4000 | 8000
| 4 | Present Draft Coastal Zone Management Plan to Councillors. |  | 1500 | 0 | 500 | 1000
|  |  | Total: | 16500 | 0 | 5500 | 11000
No | Milestone
4 | Finalise Coastal Management Program
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Summary of changes required provided to consultant. |  | 1500 | 0 | 500 | 1000
| 2 | Update Coastal Zone Management Plan in response to comments. |  | 12000 | 0 | 4000 | 8000
| 3 | Council approval of changes made by consultant. |  | 850 | 0 | 283 | 567
| 4 | Final Coastal Zone Management Plan submitted to Council. |  | 12000 | 0 | 4000 | 8000
|  |  | Total: | 26350 | 0 | 8783 | 17567
No | Milestone
5 | Final acquittal
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Submit acquittal documents to DPIE |  | 0 | 0 | 0 | 0
|  |  | Total: | 0 | 0 | 0 | 0