## Sheet1
Department of Planning, Industry and Environment
Work Plan - Coastal Hazard Study
Program Name: |  | Coastal and Estuary Management Grants - Planning stream (CEMP)
Grant Recipient:
Project Name:
Grant Reference No:
Grant Offer: |  |  | Total Project Cost:
Funding Term Completion Date: |  |  | Funding Level/Ratio:
Project Manager: |  |  | Phone: |  | Date Prepared:
Milestone Number | Milestone | Activities | Outputs | Projected Milestone Completion Date (dd/mm/yyyy) | Total Estimated Milestone Cost (all contributions) GST exclusive | Estimated Milestone Payment Amount (Government contribution only) GST exclusive
1 | Define project scope and engage consultant | Collate available information and define scope of works*. Prepare project brief*. Release brief for professional services*. Tender process and approval*. Engage consultant. Inception meeting. | Brief specifying scope of works completed. Consultant engaged. Inception meeting held.
2 | Draft Coastal Hazard Study | Literature and information review. Obtain data, e.g. LiDAR. Assess coastal hazards – beach erosion, shoreline recession, entrance instability, coastal and tidal inundation, cliff/slope instability, estuarine foreshore/bank erosion. Coastal Ecosystem Health Assessment. Submit Draft Coastal Hazard Study to Council and DPIE for review prior to public exhibition. Present Draft Coastal Hazard Study to Councillors. Incorporate changes required by Council. | Draft Coastal Hazard Study completed and approved by Council for public exhibition**.
3 | Consultation | Ciculate Draft Coastal Hazard Study to stakeholders for comment. Publicly exhibit Draft Coastal Hazard Study**. Conduct community workshops. | Stakeholders and community familiar with Draft Coastal Hazard Study (e.g. XX community workshops held). Stakeholders and community provide feedback on Draft Coastal Hazard Study (e.g. XX submissions received).
4 | Finalise Coastal Hazard Study | Summary of changes required provided to consultant. Update Coastal Hazard Study in response to comments. Council approval of changes made by consultant. Final Coastal Hazard Study submitted to Council. | Coastal Hazard Study completed.
| Final Report |  | Grant acquitted |  | N/A
| Totals |  |  |  | 0 | 0
*Ineligible for funding as defined as 'Recipient's Core Activities' (refer to clause 2.2 of Funding Agreement) **Please note that it is not a requirement to publicly exhibit a Coastal Hazard Study and seek Council's approval, however, some Councils may choose to do so.
Submit to Grants Unit via email at coastalestuary.floodgrants@environment.nsw.gov.au
For office use only
I have reviewed this Work Plan and approve / do not approve it (delete whichever is not applicable)
Name |  | Date | Signature/Email approval
Department of Planning, Industry and Environment, Locked Bag 5022, Parramatta NSW 2124. Phone: 1300 361 967 (environment and national parks enquiries); email: info@environment.nsw.gov.au; website: www.environment.nsw.gov.au.