## Workplan
Workplan |  | Application Identifier: | 2021/FPM/0017 | Project Title: | Sample Flood Application
Project Outcomes
No. | Outcome | Description
1 | Flood risk management study and plan | Produce a FRMSP to identify risk management options to address the flood risk to over 85 properties within the Sample catchment
2 | Reduce risk of flooding | Reduce the risk of flooding bu identifying the most appropriate planning controls and required emergency response .
3 | Community engagement and awareness | Gaining the engagement of the community in managing flood risk
Project Schedule
No. | Milestone | Start | Finish | Outcome IDs
1 | Data collection and analysis | 2020-11-16 | 2021-01-29 | 1
| No. | Activities | Activity Type | Start | Finish
| 1 | FRM committee inception meeting | Scoping impact / identifying the risk | 2020-11-16 | 2020-11-27
| 2 | Data collection, update model and flood level survey (optional) | Scoping impact / identifying the risk | 2020-11-16 | 2021-01-29
No. | Milestone | Start | Finish | Outcome IDs
2 | Flood damages and hazard identification | 2021-04-02 | 2021-04-16 | 1, 3
| No. | Activities | Activity Type | Start | Finish
| 1 | Flood damages assessment | Scoping impact / identifying the risk | 2021-04-02 | 2021-04-16
| 2 | Flood planning measures and mapping | Scoping impact / identifying the risk | 2021-04-02 | 2021-04-16
| 3 | Progress Report | Scoping impact / identifying the risk | 2021-04-16 | 2021-04-16
No. | Milestone | Start | Finish | Outcome IDs
3 | Public exhibition of Draft FRMSP | 2021-04-02 | 2021-04-16 | 1, 3
| No. | Activities | Activity Type | Start | Finish
| 1 | FRM committee meeting | Scoping impact / identifying the risk | 2021-04-02 | 2021-04-02
| 2 | Agency consultation | Measuring reach | 2021-04-05 | 2021-04-14
| 3 | Draft FRMSP on exhibition | Scoping impact / identifying the risk | 2021-04-16 | 2021-04-16
No. | Milestone | Start | Finish | Outcome IDs
4 | Final FRMSP | 2021-04-19 | 2021-07-22 | 2, 3
| No. | Activities | Activity Type | Start | Finish
| 1 | Assess submissions of DRAFT | Scoping impact / identifying the risk | 2021-04-19 | 2021-04-30
| 2 | FRM Committee meeting | Scoping impact / identifying the risk | 2021-05-17 | 2021-05-17
| 3 | Final FRMSP to Council for adoption | Scoping impact / identifying the risk | 2021-06-16 | 2021-07-08
No. | Milestone | Start | Finish | Outcome IDs
5 | Final Report | 2022-03-31 | 2022-03-31 | 1, 2, 3
| No. | Activities | Activity Type | Start | Finish
| 1 | Flood Risk Management Study and Plan adopted | Scoping impact / identifying the risk | 2022-03-31 | 2022-03-31
|  | Handover of data to DPIE | Scoping impact / identifying the risk | 2022-03-31 | 2022-03-31
Project Measures
No. | Milestone
1 | Flood Risk Management Study and Plan
| No. | Activities | Activity Type
| 1 | Flood Risk Management Study and Plan adopted | Scoping impact / identifying the risk
|  |  | Measure | Expected Output | Unit
|  |  | Flood Study completed | 0 | Yes/No
|  |  | Investigation/design completed for evacuation management | 0 | Number
|  |  | Investigation/design completed for flood warning | 0 | Number
|  |  | Investigation/design completed for voluntary purchase and house raising | 0 | Number
|  |  | Investigation/design work progressing to implementation | 0 | No
|  |  | Number of properties found to be flood impacted in 1 % Annual Exceedance Probability event | 85 | number
|  |  | Number of properties within the flood study area | 1205 | Number
|  |  | Floodplain risk management study and plan completed | 1 | Yes
|  |  | Number of high priority floodplain management measures identified | 8 | Number
|  |  | Number of medium priority floodplain management measures identified | 8 | Number
|  |  | Number of low priority floodplain management measures identified | 15 | Number
|  |  | Floodplain risk management study and plan status | 1 | Completed and adopted
|  |  | Investigation/design completed for structural works | 0 | Number
Project Budget |  | Selected Ratio: | 0.3333
|  |  | Whole Total: | 126450 | 0 | 42152 | 84298
No | Milestone
1 | Data collection and analysis
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | FRM committee inception meeting | Meeting attendance | 500 | 0 | 167 | 333
| 2 | Data collection, update model and flood level survey (optional) | Consultant | 42500 | 0 | 14167 | 28333
|  |  | Total: | 43000 | 0 | 14334 | 28666
No | Milestone
2 | Flood damages and hazard identification
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Flood damages assessment | Consultant | 27500 | 0 | 9167 | 18333
| 2 | Flood planning measures and mapping | Consultant | 39800 | 0 | 13267 | 26533
| 3 | Progress Report | Consultant | 5500 | 0 | 1833 | 3667
|  |  | Total: | 72800 | 0 | 24267 | 48533
No | Milestone
3 | Public exhibition of Draft FRMSP
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | FRM committee meeting | Meeting attendance | 500 | 0 | 167 | 333
| 2 | Agency consultation | Government Agencies | 0 | 0 | 0 | 0
| 3 | Draft FRMSP on exhibition | Public exhibition attendance | 1750 | 0 | 583 | 1167
|  |  | Total: | 2250 | 0 | 750 | 1500
No | Milestone
4 | Final FRMSP
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Assess submissions of DRAFT | Consultant | 5900 | 0 | 1967 | 3933
| 2 | FRM Committee meeting | Meeting attendance | 500 | 0 | 167 | 333
| 3 | Final FRMSP to Council for adoption | Consultant | 2000 | 0 | 667 | 1333
|  |  | Total: | 8400 | 0 | 2801 | 5599
No | Milestone
5 | Flood Risk Management Study and Plan
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Flood Risk Management Study and Plan adopted | Output only | 0 | 0 | 0 | 0
|  |  | Total: | 0 | 0 | 0 | 0