## Workplan Summary
Workplan |  | Application Identifier: | 2022/FMP/0002 | Project Title: | Sample FRMSP flood application
Note: Cells have been formatted from original output.
Project Summary
No. | Milestone |  | Start | Finish
1 | Data collection and analysis |  | 21/09/2022 | 15/12/2022
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | FRM committee inception meeting, | 21/09/2022 | 15/12/2022 | 333 | 167 | 0 | 500
| 2 | Data collection, update model and flood level survey (optional) | 21/09/2022 | 15/12/2022 | 28333 | 14167 | 0 | 42500
|  |  |  | Total: | 28666 | 14334 | 0 | 43000
No. | Milestone |  | Start | Finish
2 | Flood damages and hazard identification |  | 1/01/2023 | 25/01/2023
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Flood damages assessment | ​01/01/2023 | 25/01/2023 | 18333 | 9167 | 0 | 27500
| 2 | Flood planning measures and mapping | ​01/01/2023 | 25/01/2023 | 26533 | 13267 | 0 | 39800
| 3 | Progress Report | 11/01/2023 | 25/01/2023 | 3667 | 1833 | 0 | 5500
|  |  |  | Total: | 48533 | 24267 | 0 | 72800
No. | Milestone |  | Start | Finish
3 | Public exhibition of Draft FRMSP |  | 25/01/2023 | 20/03/2023
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | FRM committee meeting | 25/01/2023 | 20/03/2023 | 333 | 167 | 0 | 500
| 2 | Agency consultation | 25/01/2023 | 10/02/2023 | 0 | 0 | 0 | 0
| 3 | Draft FRMSP on exhibition | ​05/03/2023 | 20/03/2023 | 1167 | 583 | 0 | 1750
|  |  |  | Total: | 1500 | 750 | 0 | 2250
No. | Milestone |  | Start | Finish
4 | Final FRMSP |  | 20/03/2023 | 10/07/2023
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Assess submissions of DRAFT | 20/03/2023 | 10/04/2023 | 3933 | 1967 | 0 | 5900
| 2 | FRM Committee meeting | 10/04/2023 | 10/05/2023 | 333 | 167 | 0 | 500
| 3 | Final FRMSP to Council for adoption | 10/05/2023 | 10/07/2023 | 1333 | 667 | 0 | 2000
|  |  |  | Total: | 5600 | 2800 | 0 | 8400
No. | Milestone |  | Start | Finish
5 | Final Report |  | 10/07/2023 | 2023-11-15
| No. | Activities | Start | Finish | Grant Contribution | Grantee Contribution | Partner Contribution | Total
| 1 | Flood Risk Management Study and Plan adopted and Handover of data to DPE | 10/07/2023 | 15/11/2023 | 0 | 0 | 0 | 0
|  |  |  | Total: | 0 | 0 | 0 | 0
|  |  |  | Overall Total: | 84299 | 42151 | 0 | 126450

## Workplan
Workplan |  | Application Identifier: | 2022/FMP/0002 | Project Title: | Sample catchment FRMSP
Project Outcomes
No. | Outcome | Description
1 | Flood risk management study and plan | Produce a FRMSP to identify risk management options to address the flood risk to over 85 properties within the Sample catchment
2 | Reduce risk of flooding | Reduce the risk of flooding by identifying the most appropriate planning controls and required emergency response.
3 | Community engagement and awareness | Gaining the engagement of the community in managing flood risk
Project Schedule
No. | Milestone |  | Start | Finish | Outcome IDs
1 | Data collection and analysis |  | 21/09/2022 | 15/12/2022 | 1
| No. | Activities | Start | Finish
| 1 | FRM committee inception meeting, | 21/09/2022 | 15/12/2022
| 2 | Data collection, update model and flood level survey (optional) | 21/09/2022 | 15/12/2022
2 | Flood damages and hazard identification |  | 1/01/2023 | 25/01/2023 | 1
| No. | Activities | Start | Finish
| 1 | Flood damages assessment | 1/01/2023 | 25/01/2023
| 2 | Flood planning measures and mapping | 1/01/2023 | 25/01/2023
| 3 | Progress Report | 11/01/2023 | 25/01/2023
3 | Public exhibition of Draft FRMSP |  | 25/01/2023 | 20/03/2023 | 1, 3
| No. | Activities | Start | Finish
| 1 | FRM committee meeting | 25/01/2023 | 20/03/2023
| 2 | Agency consultation | 25/01/2023 | 10/02/2023
| 3 | Draft FRMSP on exhibition | 5/03/2023 | 20/03/2023
4 | Final FRMSP |  | 20/03/2023 | 10/07/2023 | 2, 3
| No. | Activities | Start | Finish
| 1 | Assess submissions of DRAFT | 20/03/2023 | 10/04/2023
| 2 | FRM Committee meeting | 10/04/2023 | 10/05/2023
| 3 | Final FRMSP to Council for adoption | 10/05/2023 | 10/07/2023
5 | Final Report |  | 10/07/2023 | 15/11/2023 | 1, 2, 3
| No. | Activities | Start | Finish
| 1 | Flood Risk Management Study and Plan adopted and Handover of data to DPE | 10/07/2023 | 15/11/2023
Project Measures
Milestone
5 | Final Report
| No. | Activities | Activity Type | Measure | Expected Output | Unit
| 1 | Flood Risk Management Study and Plan adopted and Handover of data to DPE | Scoping impact / identifying the risk | Flood Study completed | 0 | Yes/No
| 1 | Flood Risk Management Study and Plan adopted and Handover of data to DPE | Scoping impact / identifying the risk | Flood Study completed | 0 | Yes/No
|  |  |  | Number of properties found to be flood impacted in 1 % Annual Exceedance Probability event | 85 | Number
|  |  |  | Number of properties within the flood study area | 1205 | Number
|  |  |  | Floodplain risk management study and plan completed | 1 | Yes/No
|  |  |  | Number of high priority floodplain management measures identified | 8 | Number
|  |  |  | Number of medium priority floodplain management measures identified | 8 | Number
|  |  |  | Number of low priority floodplain management measures identified | 15 | Number
|  |  |  | Floodplain risk management study and plan status | 1 | Completed and adopted
|  |  |  | Investigation/design completed for structural works | 0 | Number
|  |  |  | Investigation/design completed for evacuation management | 0 | Number
|  |  |  | Investigation/design completed for flood warning | 0 | Number
|  |  |  | Investigation/design completed for voluntary purchase and house raising | 0 | Number
|  |  |  | Investigation/design work progressing to implementation | 0 | Yes/No
Project Budget |  | Selected Ratio: | 33% 2:1
|  |  | Whole Total: | 126450 | 0 | 42151 | 84299
No | Milestone
1 | Data collection and analysis
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | FRM committee inception meeting, | Meeting attendance | 500 | 0 | 167 | 333
| 2 | Data collection, update model and flood level survey (optional) | Consultant | 42500 | 0 | 14167 | 28333
|  |  | Total: | 43000 | 0 | 14334 | 28666
No | Milestone
2 | Flood damages and hazard identification
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Flood damages assessment | Consultant | 27500 | 0 | 9167 | 18333
| 2 | Flood planning measures and mapping | Consultant | 39800 | 0 | 13267 | 26533
| 3 | Progress Report | Consultant | 5500 | 0 | 1833 | 3667
|  |  | Total: | 72800 | 0 | 24267 | 48533
No | Milestone
3 | Public exhibition of Draft FRMSP
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | FRM committee meeting | Meeting attendance | 500 | 0 | 167 | 333
| 2 | Agency consultation | Government Agencies | 0 | 0 | 0 | 0
| 3 | Draft FRMSP on exhibition | Public exhibition attendance | 1750 | 0 | 583 | 1167
|  |  | Total: | 2250 | 0 | 750 | 1500
No | Milestone
4 | Final FRMSP
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Assess submissions of DRAFT | Consultant | 5900 | 0 | 1967 | 3933
| 2 | FRM Committee meeting | Meeting attendance | 500 | 0 | 167 | 333
| 3 | Final FRMSP to Council for adoption | Consultant | 2000 | 0 | 667 | 1333
|  |  | Total: | 8400 | 0 | 2801 | 5599
No | Milestone
5 | Final Report
| No | Activities | Description | Total | Partner Contribution | Grantee Contribution | Grant Contribution
| 1 | Flood Risk Management Study and Plan adopted and Handover of data to DPE | Output only | 0 | 0 | 0 | 0
|  |  | Total: | 0 | 0 | 0 | 0