## Sheet1
Department of Planning, Industry and Environment
Work Plan - Investigation and Design Project
Program name: |  | Floodplain Management Program (FM) / Floodplain Risk Management Grants Scheme (FGS)
Grant recipient:
Project title:
Grant reference no. |  |  | Funding level / ratio:
Current total project cost: |  |  | Proposed total project cost:
Current maximum funding amount: |  |  | Proposed maximum funding amount:
Current funding term completion date: |  |  | Proposed funding term completion date:
Project manager: |  |  | Phone: |  | Date prepared: |  | Version no.
Milestone Number | Milestone | Activities | Outputs | Projected Milestone Completion Date (dd/mm/yyyy) | Total Estimated Milestone Cost (all contributions) GST exclusive | Estimated Milestone Payment Amount (Government contribution only) GST exclusive
1 | Data review | FRM committee inception meeting and site inspection. Preliminary data review and collection of additional data as required. Progress report Stage 1^. FRM committee meetings. | Stage 1 - Progress Report - data review and consultation - completed.
2 | Concept Design Report* | Hydrologic/hydraulic analysis (design flood levels, freeboard, impacts & mitigation options assessments). Preliminary layout survey. Preliminary geotechnical assessment. Environmental overview. Levee options assessment. Community forum & agency consultation. Concept design report Stage 2^. | Hydrologic and hydraulic analysis undertaken. Preliminary layout survey and geotechnical assessment completed. Stage 2 - Concept Design Report - completed.
3 | Preliminary Design Report* | Additional layout survey. Additional geotechnical assessment. Environmental assessment. Levee options assessment. Cost-benefit analysis. Preliminary design and draft documentation. Community forum & agency consultation. Draft Preliminary Design Report for exhibition^. FRM committee meeting. | Detailed hydrologic and hydraulic analysis undertaken. All other additional information obtained and assessed, such as environmental, geotechnical, cost-benefit. Draft Preliminary Design Report finalised for exhibition.
4 | Exhibition on draft Design and documentation | Exhibit draft Design and associated documentation (if desired) by Council. | Draft Preliminary Design Report publicly exhibited. XX community forums / consultation sessions held.
5 | Final Detailed Design and Documentation | Assess submissions and prepare final detailed designs and documentation (note: include hold point period into the activity and milestone due date). FRM committee meetings. Detailed design and documentation report for Council approval^. | Public submissions assessed. Draft detailed designs and documentation prepared. XX community forums / consultation sessions held. Draft detailed designs and documentation prepared for Council.
6 | Completion of Investigation and Design Project** | Council adopts final detailed design and documentation^. Handover of study material. | Final detailed design adopted by Council. Final detailed design, documentation and study materials provided to DPIE.
| Final Report |  | Grant acquitted |  | N/A
| Totals |  |  |  | 0 | 0
*In some cases, Milestones 2 and 3 may be combined depending on the type of project and the level of detail provided in the Floodplain Risk Management Study and Plan. **The activities and outputs under this milestone may be incorporated into Milestone 4 in instances where consultants are not paid a final instalment following adoption of the design by Council. ^Include hold point period into the milestone due date.
Submit to Grants Unit via email at coastalestuary.floodgrants@environment.nsw.gov.au
For office use only
I have reviewed this Work Plan and approve / do not approve it (delete whichever is not applicable)
Name |  | Date | Signature/Email approval
Department of Planning, Industry and Environment, Locked Bag 5022, Parramatta NSW 2124. Phone: 1300 361 967 (environment and national parks enquiries); email: info@environment.nsw.gov.au; website: www.environment.nsw.gov.au.