## Introduction
MEASUREMENT AND VERIFICATION - M&V PLANNING TOOL
THIS TOOL
This M&V planning tool has been developed to assist M&V planners capture and incorporate the various M&V design elements. The template is presented in a spreadsheet for ease of calculations, with the following contents:
Worksheet Tab | Purpose
M&V Planning Process | Describe the M&V process and corresponding use of this tool
ECM Project Background | To capture details for the site and ECM, including the estimated project benefits, implementation plan and key stakeholders
M&V Requirements | To capture the M&V requirements key considerations, desired outcomes and success criteria, as well as the M&V project details.
M&V Design | To capture the essential elements of the M&V Plan. This includes preferred M&V Option, measurement boundary definition, details of key parameters, and process information relating to conducting measurements, calculating saving and uncertainty.
M&V Budget | To prepare a project budget, based on the tasks, resources, equipment and other needs. The final figure is measured against the ECM project costs and savings as a sanity check.
M&V Tasks | To capture the step-by-step list of tasks, and allocation of resources
M&V Timing | A Gantt Chart based timeline, where tasks are given a start and completion date, so that the overall project timeline can be developed.
M&V OPERATIONAL GUIDE
Your Guide to successful M&V projects
The Measurement and Verification (M&V) Operational Guide has been developed to help M&V practitioners, business energy savings project managers, government energy efficiency program managers and policy makers translate M&V theory into successful M&V projects.
By following this guide you will be implementing the International Performance Measurement and Verification Protocol (IPMVP) a typical M&V process. Practical tips, tools and scenario examples are provided to assist with decision making, planning, measuring, analysing and reporting outcomes.
But what is M&V exactly?
M&V is the process of using measurement to reliably determine actual savings for energy, demand, cost and greenhouse gases within a site by an Energy Conservation Measure (ECM). Measurements are used to verify savings, rather than applying deemed savings or theoretical engineering calculations, which are based on previous studies, manufacturer-provided information or other indirect data. Savings are determined by comparing post-retrofit performance against a ‘business as usual’ forecast.
Across Australia the use of M&V has been growing, driven by business and as a requirement in government funding and financing programs. M&V enables:
- calculation of savings for projects that have high uncertainty or highly variable characteristics
- verification of installed performance against manufacturer claims
- a verified result which can be stated with confidence and can prove return on investment
- demonstration of performance where a financial incentive or penalty is involved
- effective management of energy costs
- the building of robust business cases to promote successful outcomes
In essence, Measurement and Verification is intended to answer the question, “how can I be sure I’m really saving money?”
Using the M&V Operational Guide
The M&V Operational Guide is structured in three main parts; Process, Planning and Applications.
Process Guide: The Process Guide provides guidance that is common across all M&V projects. Practitioners new to M&V should start with the Process Guide to gain an understanding of M&V theory, principles, terminology and the overall process.
Planning Guide: The Planning Guide is designed to assist both new and experienced practitioners to develop a robust M&V Plan for your energy savings project, using a step-by-step process for designing a M&V project.
Applications Guides: Seven separate application-specific guides provide new and experienced M&V practitioners with advice, considerations and examples for technologies found in typical commercial and industrial sites. The Applications Guides should be used in conjunction with the Planning Guide to understand application-specific considerations and design choices.
Application Guides are available for:
- Lighting
- Motors, pumps and fans
- Commercial heating, ventilation and cooling
- Commercial and industrial refrigeration
- Boilers, steam and compressed air
- Whole buildings
- Renewables and cogeneration
The guide is intended to be used as per the following diagram:
COPYRIGHT NOTICE
© Copyright State of NSW and Office of Environment and Heritage With the exception of photographs, the State of NSW and Office of Environment and Heritage are pleased to allow this material to be reproduced in whole or in part for educational and non-commercial use, provided the meaning is unchanged and its source, publisher and authorship are acknowledged. Specific permission is required for the reproduction of photographs. The Office of Environment and Heritage (OEH) has compiled this guideline in good faith, exercising all due care and attention. No representation is made about the accuracy, completeness or suitability of the information in this publication for any particular purpose. OEH shall not be liable for any damage which may occur to any person or organisation taking action or not on the basis of this publication. Readers should seek appropriate advice when applying the information to their specific needs. Every effort has been made to ensure that the information in this document is accurate at the time of publication. However, as appropriate, readers should obtain independent advice before making any decision based on this information. Published by: Office of Environment and Heritage NSW 59 Goulburn Street, Sydney NSW 2000 PO Box A290, Sydney South NSW 1232 Phone: (02) 9995 5000 (switchboard) Phone: 131 555 (environment information and publications requests) Phone: 1300 361 967 (national parks, climate change and energy efficiency information, and publications requests) Fax: (02) 9995 5999 TTY: (02) 9211 4723 Email: info@environment.nsw.gov.au Website: www.environment.nsw.gov.au Report pollution and environmental incidents Environment Line: 131 555 (NSW only) or info@environment.nsw.gov.au See also www.environment.nsw.gov.au OEH 2012/0999 December 2012

## M&V Planning Process
MEASUREMENT AND VERIFICATION - PLANNING PROCESS
INTRODUCTION
The suggested M&V planning process listed below can be used as a basis for developing a M&V plan. A full description of this process is provided in the M&V Operational Guide: Planning Guide.
PLANNING PROCESS | PLANNING TOOL REFERENCE
Process Step | ECM Project Background | M&V Requirements | M&V Plan | M&V Budget | M&V Tasks | M&V Timing
| Enter the details of key stakeholders | Capture the M&V requirements key considerations, desired outcomes and success criteria, as well as the M&V project details. | Enter the details of the M&V project manager and project team. | Enter the names of resources who will be conducting tasks within the M&V project
Enter the details of the site and ECM, including implementation dates, milestones and potential issues
Enter the details of the M&V requirements and desired outcomes. This includes the project scope and objective, considerations, risks, deliverables, and measures of success.
Enter the preliminary budget figure.
Enter the details of design and planning decisions, including notes and assumptions
|  |  | Enter details of the equipment requirements, proposed techniques for collecting and manipulating data, and for calculating savings. | List the equipment/software/external expertise that has to be procured.
[5 empty] | Document the step-by-step list of tasks in order, allocating resources and budget time allocation. | Starting with the ECM implementation date, determine the start and end dates for each task.
Finalise the budget by completing cost elements for labour, equipment and other expenses.
Review the requirements within this tab, against the M&V design presented in the Plan, Budget and Timing tabs.
The completed workbook contains the M&V planning elements. Contents may be transferred into proposals or presentations if required to assist with business case approval.

## ECM Project Background
ENERGY CONSERVATION MEASURE - PROJECT BACKGROUND
SITE DETAILS
Site Name
Address
Site Overview
DESCRIPTION OF THE ECM PROJECT(S) BEING IMPLEMENTED
Description of ECM Project being implemented
Estimated Project Benefits | Energy (GJ) | Cost ($) | Greenhouse (t. CO2-e)
| 0 | 0 | 0
Estimated Implementation Cost ($) | 0
Implementation Plan Description
Key Dates
Key Stakeholders/Contacts | Name / Company | Role | Contact

## M&V Requirements
MEASUREMENT AND VERIFICATION - PROJECT SUMMARY AND REQUIREMENTS
PROJECT INFORMATION
Project Name |  | Project #
Project manager |  | Last Updated
Project Team | Name / Company | Role | Contact
[Resource 1]
[Resource 2]
[Resource 3]
[Resource 4]
[Resource 5]
[Resource 6]
Preliminary Budget
SUMMARY
Objectives
Scope | In Scope | Out of Scope
Deliverables | Deliverable | Due Date
Key considerations | Assumptions & Constraints | Risks
|  | Category | Risk Description
Success criteria | 1 -
2 -
3 -
4 -
5 -
Note on B25: Note A for assumptions, C for constraints
Note on C26: This is a field you can use to identify risks by categories such as technological, personnel, etc.

## M&V Design
MEASUREMENT AND VERIFICATION - M&V DESIGN
PROJECT INFORMATION
Project Name | 0 | Project # | 0
Project manager | 0 | Last Updated | 0
M&V APPROACH
M&V Option Selected
Desired Accuracy (%)
Overall Approach
Baseline Period
Post-Retrofit Period
MEASUREMENT BOUNDARY
Description of Measurement Boundary
Linked documents or drawings
KEY PARAMETERS AND VARIABLES
Key Parameters to be measured | Parameter | Measurement period and duration | Method for Collecting Data
Other Parameters to consider | Parameter | Reason for consideration | Method for Considering/Estimating Data
Baseline Adjustments and Independent Variables that affect Energy Use within Boundary | Type of Adjustment/Variable | Routine/Non Routine | Method for Adjusting baseline
Potential interactive effects identified | Interactive Effect | Materiality | Agreed Approach
EQUIPMENT REQUIREMENTS
Measurement Equipment | Equipment | To be sourced from (who/when/how) | Period required
CALCULATING RESULTS
Approach/method for calculating energy and demand savings
Approach/method for calculating savings uncertainty
Approach for calculating cost savings and greenhouse gas emissions
Approach for extrapolating results

## M&V Budget
MEASUREMENT AND VERIFICATION - BUDGET PLANNER
PROJECT INFORMATION
Project Name | 0 |  | Project # | 0
Project manager | 0 |  | Last Updated | 0
BUDGET DETAILS
Internal Expenses
Resource (insert name/role) | Hourly Rate | # Hours | Total Cost |  | Notes/Comments
[Resource 1] | 140 | 1 | 140
[Resource 2] | 120 | 0 | 0
[Resource 3] | 80 | 0 | 0
[Resource 4] | 90 | 0 | 0
[Resource 5] | 80 | 0 | 0
[Resource 6] | 80 | 0 | 0
Other Internal Expenses |  |  | Total Cost
Enter expense type |  |  | 0
Enter expense type |  |  | 0
Enter expense type |  |  | 0
Total Internal Expenses |  |  |  | 140
External Expenses
External Labour Costs (Consultants, Contractors) |  |  | Total Cost
Enter external labour cost item |  |  | 0
Enter external labour cost item |  |  | 0
Enter external labour cost item |  |  | 0
Other Expenditure (eg equipment) | Qty | Rate | Total Cost
Enter expense type |  |  | 0
Enter expense type |  |  | 0
Enter expense type |  |  | 0
Total External Expenses |  |  |  | 0
Total Budget |  |  |  | 140
M&V BUDGET AS A PROPORTION OF PROJECT COST/SAVINGS
Project Savings / Implementation Cost |  |  |  | $ | M&V Percentage of Cost
Estimated Annual Project Savings |  |  |  | 0 | #NAME?
Estimated Implementation Cost |  |  |  | 0 | #NAME?
Note on F16: Include additional rows for resources, expenses and external costs by unhiding rows and adding more rows as needed

## M&V Tasks
MEASUREMENT AND VERIFICATION - TASK LIST
PROJECT INFORMATION
Project Name | 0 | Project # | [6 empty] | 0
Project manager | 0 | Last Updated | [6 empty] | 0
Resource |  | [Resource 1] | [Resource 2] | [Resource 3] | [Resource 4] | [Resource 5] | [Resource 6] | Total | Notes
Total Hours |  | 1 | 0 | 0 | 0 | 0 | 0 | 1
TASK LIST
| Project Management | [6 empty] | 1 | 100%
1 | Initiate M&V project using internal processes | 1 | [5 empty] | 1
2 | Obtain information regarding the ECM(s) to be implemented | [6 empty] | 0
3 | Establish M&V project team | [6 empty] | 0
4 | Develop preliminary budget estimate and evaluate cost/benefit | [6 empty] | 0
5 | Close out M&V project using internal processes | [6 empty] | 0
6 | [7 empty] | 0
| Develop M&V Plan | [6 empty] | 0 | 0%
1 | Conduct a meeting with site contact, contractor and project manager to agree on approach | [6 empty] | 0
2 | Review project drawings to determine measurement boundary | [6 empty] | 0
3 | Review each ECM and decide on the appropriate M&V option, and key measurement parameter(s) | [6 empty] | 0
4 | Finalise M&V budget and timing | [6 empty] | 0
5 | Document agreed approach using standard M&V Plan proforma | [6 empty] | 0
6 | [7 empty] | 0
| Collect Baseline Data | [6 empty] | 0 | 0%
1 | Prepare production data tracking sheet and discuss with equipment operator | [6 empty] | 0 | hard copy data entry sheet to be filled in by shift staff each hour
2 | Hire electricity data logger | [6 empty] | 0 | energy data logger to be hired for 1 week
3 | Install data logger on equipment and log for 1 week | [6 empty] | 0 | electrician to install and remove
4 | Review throughput tracker to ensure quality data collection | [6 empty] | 0 | mid-week spot-check
5 | Download logger data and check to ensure completeness | [6 empty] | 0 | use software supplied with logger to interrogate
6 | [7 empty] | 0
| Implement ECM(s) | [6 empty] | 0 | 0%
1 | Implement ECM, and establish steady-state operation | [6 empty] | 0
2 | [7 empty] | 0
| Collect Post-Retrofit Data | [6 empty] | 0 | 0%
1 | Hire electricity data logger | [7 empty] | energy data logger to be hired for 1 week
2 | Install data logger on equipment and log for 1 week | [7 empty] | electrician to install and remove
3 | Review throughput tracker to ensure quality data collection | [7 empty] | mid-week spot-check
4 | Download logger data and check to ensure completeness | [7 empty] | use software supplied with logger to interrogate
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
| Analyse Results and Calculate Savings | [6 empty] | 0 | 0%
1 | Enter hourly production data into spreadsheet | [6 empty] | 0
2 | Collate hourly energy use | [6 empty] | 0
3 | Analyse production data vs energy to develop relationship curves (before vs after) | [6 empty] | 0
4 | Use the curve to adjust the baseline figures for the production observed during the post-retrofit period | [6 empty] | 0
5 | Calculate savings by subtracting actual from adjusted baseline | [6 empty] | 0
6 | Calculate savings uncertainty | [6 empty] | 0
7 | Calculate cost and greenhouse savings | [6 empty] | 0
8 | Peer review | [6 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
| Report Outcomes | [6 empty] | 0 | 0%
1 | Extrapolate measured savings from week across the year | [6 empty] | 0
2 | Prepare and distribute M&V energy savings report | [6 empty] | 0
3 | Present findings to site and division management | [6 empty] | 0
4 | [7 empty] | 0
5 | [7 empty] | 0
6 | [7 empty] | 0
Note on B11: Add/edit/remove tasks as required.
Note on A7: Edit labels for resources in the Requirements tab.

## M&V Timing
MEASUREMENT AND VERIFICATION - TIMING
PROJECT INFORMATION
Project Name | 0 | Project # |  | 0
Project manager | 0 | Last Updated |  | 0
Task list (linked to Tasks worksheet) |  |  |  |  | Week Commencing
Item | Tasks | Total Hours | Plan Start | Plan Finish | 2012-12-31 |  |  |  |  | 2013-01-07 |  |  |  |  | 2013-01-14 |  |  |  |  | 2013-01-21 |  |  |  |  | 2013-01-28 |  |  |  |  | 2013-02-04 |  |  |  |  | 2013-02-11 |  |  |  |  | 2013-02-18 |  |  |  |  | 2013-02-25 |  |  |  |  | 2013-03-04 |  |  |  |  | 2013-03-11 |  |  |  |  | 2013-03-18 |  |  |  |  | 2013-03-25 |  |  |  |  | 2013-04-01 |  |  |  |  | 2013-04-08 |  |  |  |  | 2013-04-15 |  |  |  |  | 2013-04-22 |  |  |  |  | 2013-04-29 |  |  |  |  | 2013-05-06 |  |  |  |  | 2013-05-13 |  |  |  |  | 2013-05-20 |  |  |  |  | 2013-05-27 |  |  |  |  | 2013-06-03 |  |  |  |  | 2013-06-10 |  |  |  |  | 2013-06-17 |  |  |  |  | 2013-06-24 |  |  |  |  | 2013-07-01 |  |  |  |  | 2013-07-08 |  |  |  |  | 2013-07-15
Enter Dates | time axis 2012-12-31 to 2013-07-19
| Project Management | 1
1 | Initiate M&V project using internal processes | 1 | 2013-01-01
2 | Obtain information regarding the ECM(s) to be implemented | 0
3 | Establish M&V project team | 0
4 | Develop preliminary budget estimate and evaluate cost/benefit | 0
5 | Close out M&V project using internal processes | 0
6 |  | 0
| Develop M&V Plan | 0
1 | Conduct a meeting with site contact, contractor and project manager to agree on approach | 0
2 | Review project drawings to determine measurement boundary | 0
3 | Review each ECM and decide on the appropriate M&V option, and key measurement parameter(s) | 0
4 | Finalise M&V budget and timing | 0
5 | Document agreed approach using standard M&V Plan proforma | 0
6 |  | 0
| Collect Baseline Data | 0
1 | Prepare production data tracking sheet and discuss with equipment operator | 0
2 | Hire electricity data logger | 0
3 | Install data logger on equipment and log for 1 week | 0
4 | Review throughput tracker to ensure quality data collection | 0
5 | Download logger data and check to ensure completeness | 0
6 |  | 0
| Implement ECM(s) | 0
1 | Implement ECM, and establish steady-state operation | 0
2 |  | 0
| Collect Post-Retrofit Data | 0
1 | Hire electricity data logger | 0
2 | Install data logger on equipment and log for 1 week | 0
3 | Review throughput tracker to ensure quality data collection | 0
4 | Download logger data and check to ensure completeness | 0
5 |  | 0
6 |  | 0
7 |  | 0
8 |  | 0
9 |  | 0
10 |  | 0
| Analyse Results and Calculate Savings | 0
1 | Enter hourly production data into spreadsheet | 0
2 | Collate hourly energy use | 0
3 | Analyse production data vs energy to develop relationship curves (before vs after) | 0
4 | Use the curve to adjust the baseline figures for the production observed during the post-retrofit period | 0
5 | Calculate savings by subtracting actual from adjusted baseline | 0
6 | Calculate savings uncertainty | 0
7 | Calculate cost and greenhouse savings | 0
8 | Peer review | 0
9 |  | 0
10 |  | 0
| Report Outcomes | 0
1 | Extrapolate measured savings from week across the year | 0
2 | Prepare and distribute M&V energy savings report | 0
3 | Present findings to site and division management | 0
4 |  | 0
5 |  | 0
6 |  | 0
0
0
0
Note on F8: Enter the start date for your project timeline here
Note on B8: Once you have entered your tasks in the M&V Tasks tab, fill down cells A10:ET10 to place your tasks in the Gantt Chart
Note on D8: Enter start and end dates for each task

## M&V Results
MEASUREMENT AND VERIFICATION - REPORTED OUTCOMES
PROJECT INFORMATION
Project Name | 0 |  |  | Project # |  | 0
Project manager | 0 |  |  | Last Updated |  | 0
PROJECT BENEFITS - SUMMARY
Component | Unit of Measure | Adjusted Baseline | Post-Retrofit | Savings | Savings % | Precision % | Confidence %
Total Energy | GJ | 0 | 0 | 0 |  | 0%
Demand | kW | 0 | 0 | 0 |  | 0%
Energy and Demand Cost ($) | $ | 0 | 0 | 0
Greenhouse Gas Emissions | t. CO2-e | 0 | 0 | 0
PROJECT BENEFITS - DETAILS
Component | Unit of Measure | Adjusted Baseline | Post-Retrofit | Savings | Savings % | Precision % | Confidence %
Total Energy | GJ | 0 | 0 | 0 |  | 0%
Electricity | kWh |  |  | 0
Natural Gas | MJ |  |  | 0
other | tbc
other | tbc
Demand
Demand (kW) | kW |  |  | 0
Demand (kVA) | kVA |  |  | 0
Energy and Demand Cost ($) | $ | 0 | 0 | 0
Electricity | $ |  |  | 0
Natural Gas | $ |  |  | 0
other | $ |  |  | 0
other | $ |  |  | 0
Demand (kW) | $ |  |  | 0
Demand (kVA) | $ |  |  | 0
Greenhouse Gas Emissions | t. CO2-e | 0 | 0 | 0
Electricity | t. CO2-e | 0 | 0 | 0
Natural Gas | t. CO2-e | 0 | 0 | 0
other | t. CO2-e
other | t. CO2-e